## Sheet1
Sprint | Duration | Key Objectives | Tasks | Tech Stack | QA Activities | Success Metrics | Owner
Sprint 0 | Week 1 | Project Setup & Discovery | - Finalize scope with DNV.- Set up CI/CD pipeline.- Scan sample manuals | GitLab, Confluence | - Validate scan quality (300 DPI) | 100% environments ready | PM/Lead Eng
Sprint 1 | Week 2-3 | Manual Digitization MVP | - OCR 50% manuals.- Marine Engineer starts categorization | Tesseract, Python | - OCR accuracy ≥95%.- Peer review 20% samples | 50% data digitized | Data Team
Sprint 2 | Week 4-5 | Core App Architecture | - Role-based API development.- DB schema design | Node.js, PostgreSQL | - 100% unit test coverage | APIs pass all integration tests | Backend Team
Sprint 3 | Week 6-7 | UI Development & Data Integration | - Build task dashboard.- Connect categorized data to UI | React, Redux | - Cross-browser testing.- Lighthouse score ≥90 | 80% UI components complete | Frontend Team
Sprint 4 | Week 8-9 | End-to-End Testing | - Crew UAT sessions.- Chief Engineer reporting validation | Selenium, Jest | - ≥90% UAT pass rate.- 0 critical bugs | All P0 bugs resolved | QA Team
Sprint 5 | Week 10-11 | Deployment Prep & Training | - Production deployment.- Create training materials | Docker, AWS | - Smoke testing.- Load testing (100+ users) | 99.5% uptime SLA | DevOps
Sprint 6 | Week 12 | Go-Live & Retrospective | - Monitor live system.- Conduct team retrospective | Google Analytics | - User adoption tracking | ≥85% crew adoption in Week 1 | PM