## Slide 1: XYZ Engine Room Manual Digitization Project Plan
Problem Statement: Ships rely heavily on manual maintenance documentation stored in Engine Room manuals. These documents are often unstructured, paper-based, and not easily accessible during emergencies or routine operations. The lack of digitization leads to delays in task execution, inconsistent maintenance tracking, and potential safety hazards due to missed or improperly executed tasks. This inefficiency poses serious operational and financial risks, especially in scenarios involving critical machinery failures (e.g., water purifiers, engines).
Objective: To develop a robust, user-centric web application that digitizes the entire Engine Room manual system, enabling structured, role-specific task management and real-time monitoring. The application will integrate digitized manual content, assign maintenance responsibilities based on crew roles, and ensure daily visibility for the Chief Engineer. It aims to empower ship staff with accurate, accessible, and actionable information — reducing operational risks, improving maintenance workflows, and ultimately enhancing onboard safety and accountability.
Problem statement & Objective

## Slide 2: High Level Requirements:
Manual Digitization
OCR Processing: Convert scanned Engine Room manuals to digital text.
Categorization: Marine experts will categorize data into Jobs, Components, and Spares.
QA/QC: Multi-stage verification to ensure data accuracy.
Web Application Development
Role-Based System: Task assignment based on crew roles (e.g., Maintenance, Spare Parts).
Task Tracking: Real-time task progress, work hours, and image uploads.
Chief Engineer Dashboard: Monitor crew progress and take corrective action in real-time.
Mobile & Offline Access: Accessible across devices with offline caching.

## Slide 3: Business Drivers and Goals:
Business Drivers:
Safety: Minimize risk of life-threatening situations onboard by ensuring timely maintenance and task completion.
Operational Efficiency: Streamline task management and reduce human errors, ensuring optimal ship performance.
Financial Risk Mitigation: Prevent costly repairs and operational disruptions caused by missed maintenance tasks.
Business Goals:
100% Accurate Data: Ensure digital manuals reflect manual data with zero errors.
Role-Specific Task Management: Provide the right data and tasks to the right crew members based on their roles.
Complete Accountability: Track all tasks, working hours and completed maintenance actions for full transparency.

## Slide 4: Business and System Implications:
Business Implications:
Improved Decision Making: Real-time access to accurate task data allows better operational oversight and quick corrective actions.
Increased Crew Accountability: Real-time task logging and status tracking ensures every crew member is responsible for their assigned tasks.
Scalability: The system can expand as more manuals or tasks are added, supporting future needs.
System Implications:
Data Integrity: Ensuring 100% accurate transfer and categorization of manual data is critical to avoid safety risks.
Role-Based Access: The system must ensure data and tasks are assigned based on each crew member’s role.
High Availability: The system should be robust enough to handle 24/7 use onboard, with minimal downtime, especially in low-connectivity environments.
Security: Implement stringent security protocols to protect sensitive data and prevent unauthorized access.

## Slide 5: Engagement Type & Pricing Model:
Engagement Type:
Fixed-Price Engagement based on agreed deliverables and milestones.
Phased approach with clear checkpoints to ensure quality and progress.
Pricing Model:
Milestone-Based Payments: Payments tied to the completion of specific project phases.
  Milestone 1: OCR and Manual Categorization Completion.
  Milestone 2: Web Application Development.
  Milestone 3: Final Testing, Deployment, and Handover.

## Slide 6
Phase | Weeks | Key Activities | Deliverables | Quality Gates
Phase 1: Planning | Week 1-2 | - Manual scanning setup | - Scan quality report | - 100% manual scans at 300+ DPI
 |  | - UI/UX wireframe approval | - Signed-off prototypes | - XYZ design approval
 |  | - Marine engineer onboarding |  | 
Phase 2: Digitization | Week 3-6 | - OCR processing | - Structured Excel/CSV files | - OCR accuracy ≥98%
 |  | - Data categorization (Jobs/Components/Spares) | - Data validation report | - 100% peer-reviewed categorization
 |  | - QA validation |  | 
Phase 3: Development | Week 3-8 | - Backend API development | - Functional web app | - 100% unit test coverage
 |  | - Frontend integration | - Test automation scripts | - ≤0.5 defects/100 LOC
 |  | - Role-based logic testing |  | 
Phase 4: UAT | Week 7-8 | - Crew testing (real tasks) | - UAT sign-off document | - ≥90% user satisfaction
 |  | - Chief Engineer reporting validation | - Priority bug list | - 100% critical bugs resolved
 |  | - Bug fixes |  | 
Phase 5: Deployment | Week 9-12 | - Production rollout | - Live system | - 99.5% uptime SLA
 |  | - Crew training | - Training materials | - 100% training completion
 |  | - Documentation handover | - Support plan | 
Duration of Engagement

## Slide 7: Proposed Solution Flow
Digital Transformation
Define Scope and Objective
Select Tech Stack , Architecture, OCR methods for Data extraction
UI/UX
Develop MVP( Sprint and Review , includes client feedback)
Thirdparty tools Integration( OCR )
Testing and UAT
Deployment
Monitoring and Maintenence

## Slide 8: Plan and Execution:
Methodology:
Hybrid Approach: Combines Waterfall for manual digitization and Agile for web app development.
Waterfall: Sequential process for OCR and categorization to ensure accuracy.
Agile Scrum: Iterative development for the web app, enabling regular feedback and flexibility.
Tools:
JIRA: For task management, sprint tracking, and backlog grooming.
Confluence: For documentation and team collaboration.
Miro: For brainstorming and wireframing.
Slack/MS Teams: For communication and daily standups.
TestRail: For test case management.
Postman: For API testing.

## Slide 9: Delivery management
Progress Reports: Detailed analysis of work done and work in progress and upcoming tasks.
Budget Tracking: Regular updates on financials.
Quality metrics: System performance and load testing results.
Sprint progress: A breakdown of user stories, features completed and velocity.
Risks & mitigation : Tracking and reporting of risks, impediments and planned mitigations.

## Slide 10: Metrics
OCR Accuracy: The accuracy of the OCR processing is critical. The target accuracy should be ≥99.5% for digitized data.
  Target: 99.5% accuracy in the OCRed text.
  Measurement: QA team will perform checks to compare the output with the original scanned manuals.
Task Completion Rate: Percentage of tasks completed within the assigned timeframe.
  Target: ≥95% of tasks completed on schedule.
  Measurement: Weekly progress tracking by the system, available for both crew members and the Chief Engineer.
Real-Time Monitoring: How effectively real-time monitoring occurs for task management.
  Target: Daily reporting on all active tasks and real-time status of each (completed, pending, overdue).
  Measurement: Task monitoring dashboards and alerts.
Bug & Issue Resolution Rate: Percentage of issues resolved in the sprint.
  Target: ≥90% of reported issues fixed within the sprint cycle.
  Measurement: Issue tracking system integrated with JIRA.

## Slide 11: DBT Tools & Techniques
Tesseract OCR + GPT-4
  Purpose: Extract text from scanned manuals with 98%+ accuracy
  AI Enhancement: Context-aware correction of technical terms
Python Pandas
  Purpose: Structure data into Jobs/Components/Spares
  QA: Automated rule-based validation
Application Development
Frontend: React.js (Role-based dashboards)
Backend: Node.js + PostgreSQL (Task management engine)
DevOps: Docker + AWS (Scalable deployment)

## Slide 12: Change Management Process: Change Requests (CR): Any significant changes to scope (e.g. additional features, new manual formats, or changes in roles) must be submitted as a Change Request through JIRA. Approval: Each CR will be reviewed by both the project management team and XYZ's key stakeholders. Impact Analysis: An analysis will assess how the change impacts the schedule, costs, and resources. Version Control: All changes to the codebase and system configurations will be tracked using Git, ensuring rollbacks are possible if needed. Stakeholder Communication: Regular updates and feedback loops with the Chief Engineer and XYZ stakeholders. Communication will be handled through Slack for daily interactions and email/weekly meetings for major updates.

## Slide 13: Risks & Mitigation plan
Risk | Description | Impact | Likelihood | Mitigation Strategy
OCR Accuracy Issues | OCR technology may not achieve 100% accuracy, leading to misinterpreted text. | Misclassification of data, incorrect maintenance instructions. | High | - Dual verification process: OCR output followed by marine expert categorization. - Continuous feedback loop with marine experts. - Use robust OCR tools (Azure OCR, Tesseract) with fine-tuning options. - Test scans on a subset of documents.
Data Integrity & Categorization Errors | Mis-categorization of tasks, components, and spares during the OCR process. | Incorrect task assignments, crew members missing vital data. | Medium | - Involve marine experts in categorization review. - Standardize categorization rules. - Provide training for categorization consistency.
OCR Tool Performance on Scanned Quality | Poor scan quality affects OCR processing accuracy. | Incomplete or missing data, additional manual corrections needed. | Medium | - Ensure high-quality scans (300 DPI or higher). - Pre-processing of scans to enhance quality (contrast, noise reduction). - Regular OCR performance validation with sample scans.
Role-Based Access Control (RBAC) Issues | Improper role-based access leading to unauthorized access to tasks or data. | Security breaches, unauthorized data changes. | Medium | - Define clear role-based access early in the development cycle. - Regular code reviews focused on RBAC implementation. - Penetration testing for security validation. - UAT testing with role-based access verification.
System Performance Under Load | Application performance degrades under high user load. | Slow task tracking, potential delays in task updates. | Medium | - Perform stress and load testing before deployment. - Use cloud-based infrastructure for scalability. - Optimize front-end and back-end code for performance.
Data Synchronization Issues | Failure to sync task data in low-connectivity environments. | Outdated task status, missing data for crew members. | High | - Implement offline-first capabilities with auto-sync once connectivity is restored. - Use data caching and background syncing for real-time updates. - Implement conflict resolution mechanisms for data sync errors.
Security Breaches and Data Privacy Concerns | Vulnerabilities in the web app may expose sensitive data. | Exposure of sensitive operational data, reputational damage. | Low | - Ensure encryption of data at rest and in transit (TLS/SSL). - Regular security audits and vulnerability assessments. - Implement access control and secure authentication methods (OAuth 2.0).

## Slide 14: Definition of done
For Manual Digitization:
OCR Accuracy: Data Categorization
QA & QC Pass
For Web Application Development:
Frontend Development:
  User Interface (UI) must be responsive and accessible across devices.
  All role-based views must function as intended (e.g., Crew members only see their assigned tasks).
Backend Development:
  APIs for task assignment, progress tracking, and reporting must be developed and tested.
  Real-time data processing should be capable of handling high-load scenarios.
Security & Compliance:
For Testing & Deployment:
Unit Testing
Integration Testing
UAT
Code Review & Documentation

## Slide 15: Definition of Ready
OCR Processing: Definition of Ready (DoR)
High-resolution scans (300 DPI or higher) provided.
OCR Tool Setup: OCR tools (e.g., Azure OCR, Tesseract) configured and tested for manual formats.
Data Format: Clear structure for data output (e.g., Excel, JSON).
Categorization Guidelines: Defined system for categorizing Jobs, Components, Spares.
SME Availability: Marine experts available to review and categorize data.
Test Data: Sample OCR data available for initial validation.
Web Application Development: Definition of Ready (DoR)
User Stories Defined: Well-defined user stories with clear acceptance criteria.
Wireframes & Mockups: UI/UX designs and wireframes ready for development.
Role-Based Access Setup: Defined roles and permissions (e.g., Crew, Chief Engineer).
Backend Setup: APIs, database schemas, and integrations outlined and ready.
Development Environment: Tools and environment set up for coding and testing.
Security & Compliance Requirements: Security protocols (e.g., OAuth 2.0, data encryption) established.
Testing Framework: Automated testing framework in place (unit tests, integration tests).
Integration Points: All integration points identified and ready for development.
Stakeholder Approval: Stakeholder feedback and approval received for initial designs and stories.

## Slide 16: Conclusion
This proposal outlines a clear path for a complete revamp to digital transformation and of Globomart to make an entry to the Online ecommerce world.
The agile approach will ensure a smooth transition of the company and its employee to adapt from offline to online business as both will be involved throughout the phases and will play a vital role in development of the platform with their feedback.
THANK YOU.